## Sheet1
Project | Task Item | Hours Planned | Planned Start Date | Planned End Date | Hours spent for the day | %Completed | Issue comments
BPO MIS | Database Design | 4 | 2021-03-09 | 2021-03-09 | 4 | 100%
| Model Creation | 2 | 2021-03-09 | 2021-03-09 | 2 | 90% | some more changes will come in the model
| Page Listing | 2 | 2021-03-09 | 2021-03-09 | 2 | 100%
| New Page Design | 8 | 2021-03-10 | 2021-03-10 | 8 | 95%
| Save & Edit Functionality | 8 | 2021-03-12 | 2021-03-12 | 8 | 70% | Data saved into the database.Edit functionality is not finished.Design needs to change